## 0-INSTRUCTIONS
Complete the budget tables in this file:
1. | Save this file to your computer
2. | Save the file with the .xlsx extension
Note the tabs (lower part of this screen) for these three worksheets.
1-Project Schedule (orange tab)
2-Summary Budget (red tab)
3-Detailed Budget (green tab)
ESTIMATED COSTS
Specify costs of the project by Cost Category.
Considerations:
a | Reasonable & Necessary Costs: All costs, including donated time/items, must be reasonable and necessary.
b | Volunteer hours and donated materials/supplies may be used and their documented value applied towards the total project cost.
c | Donated Services: Indicate if services are donated.
d | Fiscal Year: Budgets must be presented on a state fiscal year (July 1-June 30).
e | Applicants may NOT purchase equipment, but rather should use established equipment-use rates for equipment already owned.
f | Cost Justification: Provide a brief explanation for costs in the budget table. All expenses must be reasonable and necessary.
· Applications must be received no later than 4:00 PM (Eastern), Friday, October 21, 2022.

## 1-PROJECT SCHEDULE
PROJECT SCHEDULE
TASK (NUMBER) | ANTICIPATED START DATE MM/DD/YY | TASK DESCRIPTION | ANTICIPATED DELIVERABLE/ PRODUCT | ANTICIPATED DUE DATE MM/DD/YY

## 2-SUMMARY BUDGET
SUMMARY BUDGET TABLE
Provide TOTAL costs for each category listed below by fiscal year. When developing a budget consider an approximate start date of 04-01-23. Actual start of an approved grant is subject to many factors and may be later than 04-01-23. | [5 empty] | EXAMPLE
| State Fiscal Year | [5 empty] | State Fiscal Year
Cost Category | 04/1/23 – 6/30/23 | 7/1/23 – 6/30/24 | 7/1/24 – 6/30/25 | 7/1/25 – 6/30/26 | Total | Cost Category | 04/1/23 – 6/30/23 | 7/1/23 – 6/30/24 | 7/1/24 – 6/30/25 | 7/1/25 – 6/30/26 | Total
Personnel (salaries/wages) | 0 | 0 | 0 | 0 | 0 | Personnel (salaries/wages) | 19450 | 26600 | 7800 | 0 | 53850
Fringe Benefits | 0 | 0 | 0 | 0 | 0 | Fringe Benefits | 4243 | 5780 | 1995 | 0 | 12018
Materials and Supplies | 0 | 0 | 0 | 0 | 0 | Materials and Supplies | 40 | 0 | 0 | 0 | 40
Contractual | 0 | 0 | 0 | 0 | 0 | Contractual | 0 | 0 | 0 | 0 | 0
Travel | 0 | 0 | 0 | 0 | 0 | Travel | 550 | 1000 | 0 | 0 | 1550
Vehicle Use | 0 | 0 | 0 | 0 | 0 | Vehicle Use | 250 | 1000 | 0 | 0 | 1250
Other (specify in Detailed Budget) | 0 | 0 | 0 | 0 | 0 | Other (specify in Detailed Budget) | 45 | 60 | 0 | 0 | 105
Indirect Costs | 0 | 0 | 0 | 0 | 0 | Indirect Costs | 10899 | 14895 | 4506 | 0 | 30300
TOTAL | 0 | 0 | 0 | 0 | 0 | TOTAL | 35477 | 49335 | 14301 | 0 | 99113
| Total Match $$ | [5 empty] | Total Match $$
MATCH: Of the total budget indicate estimated value of match sources (e.g., cash, in-kind services, donated materials & supplies). | [5 empty] | MATCH: Of the total budget indicate estimated value of match sources (e.g., cash, in-kind services, donated materials & supplies). | 25125

## 5-DETAILED BUDGET (hidden)
| Description of the item or service (Examples: boulders & stone, invasive species removal) | (Examples: hours, tons) | Enter number of units | Enter cost per unit | The total cost will be calculated | What is the dollar value of match provided by the applicant and partners for each item or service? If none, enter "0". | How much money is requested as a grant?
NUMBER | ITEMS OR SERVICES | UNITS | QUANTITY | COST/UNIT | TOTAL COST | MATCH | GRANT FUNDS REQUESTED FROM PFBC
| Project Management | Hourly | 100 | 45 | 4500
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | TOTALS | 0 | 0 | 0
Comments on the budget

## 3-DETAILED BUDGET
| Detailed Cost Summary | [5 empty] | EXAMPLE: Detailed Cost Summary
CHECK IF MATCH | Reference Number | PERSONNEL | Estimated Hours | Hourly Rate ($) | Total $ | Total | CHECK IF MATCH | Reference Number | PERSONNEL | Estimated Hours | Hourly Rate | Total
| 1 |  | 0 | 0 | 0 |  |  | 1 | Professor A | 70 | 55 | 3850
| 2 |  | 0 | 0 | 0 |  |  | 2 | Grad Students | 2000 | 20 | 40000
| 3 |  | 0 | 0 | 0 |  |  | 3 | Volunteer bird watchers* | 1000 | 10 | 10000
| 4 |  | 0 | 0 | 0 |  |  | 4
| 5 |  | 0 | 0 | 0 |  |  | 5
| 6 |  | 0 | 0 | 0 |  |  | 6
| 7 |  | 0 | 0 | 0 |  |  | 7
TOTAL PERSONNEL | [5 empty] | 0 | [6 empty] | 53850
CHECK IF MATCH | Reference Number From Personnel Above | FRINGE BENEFITS |  | Enter Rate (%) (0.##) using Total for each line above | Total $ (will automatically calculate) |  | CHECK IF MATCH | Reference Number From Personnel Above | FRINGE BENEFITS |  | Rate | Total
| 1 |  |  | 0 | 0 |  |  | 1 | Professor |  | 0.55 | 2118
| 2 |  |  | 0 | 0 |  |  | 2 | Students |  | 0.21 | 8400
| 3 |  |  | 0 | 0 |  |  | 3 | Volunteers * |  | 0.15 | 1500
| 4 |  |  | 0 | 0 |  |  | 4
| 5 |  |  | 0 | 0 |  |  | 5
| 6 |  |  | 0 | 0 |  |  | 6
| 7 |  |  | 0 | 0 |  |  | 7
TOTAL FRINGE BENEFITS | [5 empty] | 0 |  | TOTAL FRINGE BENEFITS |  |  |  |  | 12017.5
CHECK IF MATCH | MATERIALS & SUPPLIES (Description) |  | Number | Cost ($) /Item | Total |  | CHECK IF MATCH | MATERIALS & SUPPLIES (Description) |  | Number | Cost ($) / Item | Total
|  |  | 0 | 0 | 0 |  |  | Waterproof Field Notebooks |  | 20 | 2 | 40
|  |  | 0 | 0 | 0 |  |  | Minnow seine (20ft x 6ft x 1/4 in mesh) |  | 1 | 250 | 250
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
TOTAL MATERIALS & SUPPLIES | [5 empty] | 0 |  | TOTAL MATERIALS & SUPPLIES |  |  |  |  | 290
CHECK IF MATCH | CONTRACTUAL (Description, include units) |  | Number | Rate ($) | Total |  | CHECK IF MATCH | CONTRACTUAL (Description, inlude units) |  | Item (number) | Rate | Total
|  |  | 0 | 0 | 0 |  |  | SCUBA gear (hours) |  | 50 | 50 | 2500
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
TOTAL CONTRACTUAL | [5 empty] | 0 |  | TOTAL CONTRACTUAL |  |  |  |  | 2500
CHECK IF MATCH | TRAVEL (Description, inlude units) |  | Number | Rate ($) | Total |  | CHECK IF MATCH | TRAVEL (Description, inlude units) |  | Item (number) | Rate | Total
|  |  | 0 | 0 | 0 |  |  | Car use, travel to study sites (miles) |  | 2000 | 0.45 | 900
|  |  | 0 | 0 | 0 |  |  | Hotel for sampling sites >70 miles from campus (Nights) |  | 10 | 65 | 650
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
TOTAL TRAVEL | [5 empty] | 0 |  | TOTAL TRAVEL |  |  |  |  | 1550
CHECK IF MATCH | VEHICLE USE |  | Number | Mileage Rate | Total |  | CHECK IF MATCH | VEHICLE USE |  | Number | Mileage Rate | Total
|  |  | 0 | 0 | 0 |  |  | 4-Wheel Drive Truck to pull boat (miles) |  | 300 | 0.45 | 135
|  |  | 0 | 0 | 0 |  |  | 10-Passenger Van to transport field crew (miles) |  | 500 | 0.35 | 175
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
TOTAL VEHICLE USE | [5 empty] | 0 |  | TOTAL VEHICLE USE |  |  |  |  | 310
CHECK IF MATCH | OTHER (Equipment Use Description. Include Units) |  | Number | Hourly Rate | Total |  | CHECK IF MATCH | OTHER (Equipment Use) (Description. Include Units |  | Number | Hourly Rate | Total
|  |  | 0 | 0 | 0 |  |  | Motor Boat Use (use of boat donated by Professor A) (Hours) |  | 300 | 0.35 | 105
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
TOTAL OTHER | [5 empty] | 0 |  | TOTAL OTHER |  |  |  |  | 105
CHECK IF MATCH | INDIRECT COSTS (Description) |  | Costs | Rate (#.##) | Total |  | CHECK IF MATCH |  | INDIRECT COSTS (Description) | Costs | Rate (#.##) | Total
|  |  | 0 | 0 | 0 |  |  |  | Personnel | 65867.5 | 0.15 | 9880.125
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
| TOTAL INDIRECT RATE |  |  |  |  | 0 |  | TOTAL INDIRECT RATE |  |  |  |  | 9880.125
| GRAND TOTAL |  |  |  |  | 0 |  | GRAND TOTAL |  |  |  |  | 97861.55
| Notes: (Include additional information, as needed): | [6 empty] | Notes: (Include additional information, as needed):
* Volunteers will be performing work at the level of a lab assistant. The salary and fringe benefit rate for a lab assistant has been used to calculate the value of the volunteer effort

## Look-up (hidden)
TRACS Level 1 | TRACS Level 2 | Performance Measure 1 | Performance Measure 2 | Performance Measure 3
(Code-Description) | (Code-Description)
1-Coordination and Administration | 1.1-Coordination and Administration | Number of meetings convened. | Number of workshops held. | Number of decisions that lead to identified outputs or outcomes.
|  | Number of grants administered. | Number of grants completed.
| 1.2-Incentives | Number of landowner agreements. | Number of acres (river miles) managed through incentive programs. | Target species population metrics (e.g., breeding pairs, relative abundance) on unmanaged and managed lands or waters, directly measured or modeled.
2-Direct Management of Natural Resources | 2.1-Create new habitat or natural processes | Number of acres or river miles converted from an initial habitat to a target habitat. | Population metrics (e.g. population, nest success) of target species measured directly or modeled. | Habitat metrics (e.g. quality, fragmentation) measured directly or modeled.
| 2.2-Dam and barrier removal | Number of dams removed. | Number of connected river miles. | Target species population metrics (e.g., relative abundance) measured directly or modeled.
| 2.3-Fire management | Number of acres burned annually by habitat type (e.g., oak-forest, barrens, grasslands). | Difference in pre- and post-burn target species population metrics (e.g., species richness) measured directly or modeled.
2.4-Fish and wildlife habitat structures
| 2.4-Fish and wildlife habitat structures (Tunnels for Amphibians & Reptiles) | Number of Tunnels constructed | Relative number of animals using the structure compared to roadkills in the same area (pre- and post-construction).
| 2.4-Fish and wildlife habitat structures (Turtle basking structures) | Number of basking structures installed. | Number of target turtles using structures.
| 2.4-Fish and wildlife habitat structures (Bat houses) | Number of bat boxes installed | Number of target bats using structures.
| 2.4-Fish and wildlife habitat structures (Exclusion Structures) | Number of caves gated | Difference in target species populations before and after installation of gates
| 2.5-Grazing/farm management | Number of acres or river miles with habitat enhancement practices. | Number of SGCN using enhanced habitats
| 2.6-Hazard or infrastructure removal | Number of hazards removed
| 2.7-Instream modification | Number of river miles with habitat enhancement practices | Number of SGCN using enhanced habitats
| 2.8-Invasive species control | Number of newly reported invasive species locations (intent of this measure is to reduce number of new sightings to -0-). | Number of new invasive species considered established (intent for this to become -0-). | Number of established invasive species removed from the Commonwealth or managed to a target level.
|  | Number of invasive species surveys conducted. | Number of Invasive Species Action Plans developed | Number of potential recreational users contacted
|  | Number of active volunteers trained | Number of people trained to a specified competency | Number of rapid-response exercises (mock or actual) in reaction to new sightings
| 2.9-Living shorelines | Linear distance of shoreline restored with native plant species
| 2.1-Planting/seeding | Number of acres planted | Habitat quality metrics (e.g., number of native plants). | Target species population metrics (e.g., relative abundance, reproductive success
| 2.11-Vegetation management | Number of acres managed | Habitat quality metrics (e.g., number of native plants). | Target species population metrics (e.g., relative abundance, reproductive success).
| 2.12-Water management | Number of acres managed to a target water level | Habitat quality as measured by relevant metrics (e.g., acres of aquatic vegetation, mudflats for shorebirds) | Target species population metrics (e.g., relative abundance, reproductive success)
| 2.13-Wildlife damage management | Number of interventions
| 2.14-Wildlife disease management | Number of interventions | Mortality rates attributed to the disease in-question
3-Data Collection and Analysis | 3.1-Database development and management | Number of records added to each database | A functional web-based Conservation Opportunity Areas decision support tool
| 3.2-Research, survey or monitoring - fish and wildlife populations | Number of surveys directed toward SGCN | Number of research projects directed toward SGCN
3.3-Research, survey or monitoring - habitat
3.4-Research, survey or monitoring - utilization
3.5-Techniques development
4-Education | 4.1-Educator/Instructor training | Number of practitioners trained with minimum certifications, as required | Number of training meetings, workshops, webinars
5-Facilities and Areas | 5.5-Cooperatively managed areas for hunting | Number of Wildlife Management Areas | Number of acres managed
| 5.6-Fish passage facilities | Number of fish passage structures constructed | Relative number of fish found upstream of a dam compared to downstream
| 5.7-Fish screening and related facilities | Number of facilities using fish screens where needed | Number of entrained fish at facilities with fish screens | Fish mortality
| 5.8-Hatcheries | Number of species “head-started” | Number of newly established, self-sustaining populations | Number of populations enhanced to a target level
| 5.15-Wildlife Management Areas | Number of Wildlife Management Areas
6-Land and Water Rights Acquisition and Protection | 6.1-Land acquisition | Number acres protected | Number of SGCN in protected acres
| 6.2-Water rights acquisition | Number of agreements | Appropriate metric for protected water (e.g., millions of gallons/day, acre-feet).
| 6.3-Conservation area designation | A functional Conservation Opportunity Area decision-support tool is anticipated by December 2018
| 6.4-Private lands agreements | Number of agreements with private landowners | Number of acres encompassed by agreements | Number of SGCN on properties with agreements
7-Law Enforcement | 7.1-Law enforcement | Number of officers trained | Number of enforcement incidents in response to specific reports of illegal harvest of SGCN or habitat destruction
8-Outreach | 8.1-Partner/stakeholder engagement | Number of meetings, workshops, conferences dedicated to the plan involving the partners, stakeholders and the public | Number of meeting, workshop, and conference attendees | Number of projects or plans develop and implemented in response outreach initiatives
9-Planning | 9.1-Land use planning | Number of green infrastructure ordinances developed | Acres designated for conservation with SGCN
| 9.3-Species and habitat management planning | Number of Species Action (Management) plans developed | Number of Species Action (Management) plans implemented | Number of Species Action (Management) plans completed
| 9.4-State Wildlife Action planning | A completed comprehensive revision of the 2015 Pennsylvania Wildlife Action Plan will be completed by 09.30.2025
10-Species Reintroduction and Stocking | 10.1-Native species restoration | Number of self-maintaining species populations re-established | Number of attempted reintroductions
| 10.2-Production and stocking for recreational purposes | Stocked animal survival | Stocked animals successfully reproducing young
11-Technical Assistance | 11.1-Environmental review | Number of consultations | Number of on-site visits | Number of SGCN element occurrences encompassed per environmental review
| 11.2-Technical assistance | Number of consultations, landowners contacted | Acres or miles of streams under habitat management guidance | Number of species or habitat management plans developed with partners